## Summary
Journey with AnandTech — Course & Lab PLAN
Mutable planning workbook: records proposals, alternatives, unresolved decisions, and review status; never overrides a locked SSOT.
Discussions logged |  |  | Open questions |  | Critical items | Sections in design
19 |  |  | 8 |  | 12 | 6
Planning workflow
Stage | Meaning | Output |  | Current planning focus
Discuss | Capture ideas and alternatives | PLAN workbook |  | 1. Resolve the host-only IP plan and bridged-versus-NAT fallback. 2. Review and lock the course section sequence. 3. Design Section 00 or Section 03 in full SSOT detail. 4. Keep all workshop milestones skip-safe. 5. Do not treat this PLAN workbook as locked authority.
Resolve | Decide open questions and trade-offs | Decision register
Draft | Convert accepted direction into exact scope | Section SSOT draft
Lock | User explicitly approves the authoritative plan | Locked SSOT
Generate | Author only the requested units and artifacts | Reviewable content
Validate | Technical, learning, scope, and editorial review | Acceptance evidence

## Plan Rules
PLAN Workbook Rules
How discussions move from proposal to locked SSOT without silent authority changes.
This workbook may contain conflicting alternatives. Only a locked SSOT can authorize final curriculum generation.
Rule | Meaning | Required behavior | Status
PLAN is mutable | Capture discussion, alternatives, rejected ideas, and unresolved choices | Update during course design | Active
SSOT is final | Contains the approved scope, order, labs, artifacts, assessments, and package name | Lock only after explicit approval | Active
No silent promotion | An accepted direction in PLAN is not automatically locked | Create/revise SSOT and request lock | Active
One section at a time | Course-wide map may exist, but deep authoring proceeds section by section | Do not generate the next section before acceptance | Active
Conflict visibility | Keep disagreements and stale proposals visible | Resolve explicitly before authoring | Active
Examples are non-authoritative | Examples provide continuity or quality evidence only | Never use examples to override locked scope | Active

## Discussion Log
Course Discussion Log
Section-wise record of requests, proposed implementation, disposition, and impact.
Add new discussion rows rather than rewriting history. Use the decision register to record the final resolution.
Date | Area | User direction / discussion | Current proposed implementation | Disposition | Affected scope | Priority
2026-09-01 | Course structure | Create sections, units, and topics for the complete zero-to-production journey | Retain detailed course map and develop one section at a time | Accepted direction | Course Map | High
2026-09-01 | Linux | Make Linux substantially more detailed and cover systemd | Expand Linux to 33 units and three milestones | Accepted direction | Section 04 | Critical
2026-09-01 | Grep | Grep is important and needs its own mini-unit with many exercises | Dedicated workshop with 40+ progressive exercises and reuse later | Accepted direction | Section 04 Unit 11 | Critical
2026-09-01 | Distributions | Compare Alpine, Debian, Ubuntu, RHEL, Arch, and required alternatives | Concept unit plus comparison workshop across nine families | Accepted direction | Section 04 Units 02-03 | High
2026-09-01 | Development insight | Teach enough development for DevOps engineers without creating a development course | Hello World to Todo using HTML/CSS/JS, FastAPI, PostgreSQL/pgvector | Accepted direction | Section 05 | Critical
2026-09-01 | IDE | Add IDE installation and environment setup | VS Code, terminal, devtools, Python venv, Remote SSH | Accepted direction | Section 05 Unit 02 | High
2026-09-01 | VirtualBox | Create a dedicated VM installation, management, automation, and initial lab section | 14-unit VirtualBox section before Linux | Accepted direction | Section 03 | Critical
2026-09-01 | Vagrant | Overview plus Vagrant code, Python, and PowerShell examples | Purpose, trade-offs, single/multi-machine examples, wrapper automation | Accepted direction | Section 03 Units 11-13 | High
2026-09-01 | Lab roles | Alpine web01; Debian cicd01; Debian mon01 | Retain roles and progressively install services in their owning sections | Accepted direction | Lab Architecture | Critical
2026-09-01 | Networking | Bridged Internet plus host-only management, persistent and SSH-accessible | Two adapters; one default route; reboot verification; exposure guidance | Accepted direction | Lab Standards | Critical
2026-09-01 | IP allocation | Requested web01 .1, cicd01 .2, mon01 .3 | Recommend host .1 and VMs .11/.12/.13 | Open | Lab Architecture | Critical
2026-09-01 | Progressive labs | Install tools as the story reaches their sections | Nginx in development/web; Git in Git; Jenkins in CI/CD; Prometheus/Grafana in monitoring | Accepted direction | Workshop Journey | High
2026-09-01 | Secure transfer | Add SCP | Dedicated SSH/SCP/SFTP/Rsync section and release workshop | Accepted direction | Section 10 | High
2026-09-01 | Ordering | Put the web/development part after Linux | VirtualBox → Linux → Development Insight → Networking | Accepted direction | Course order | Critical
2026-09-01 | Story | Main course should feel like a comic book and the labs should be practical | Episode structure with incident openings, questions, misconceptions, decisions, and close | Accepted direction | Quality Standards | Critical
2026-09-01 | Workshop | Run optional industrial labs in parallel after learners complete enough units | M00-M17 milestone journey with full/guided/skip modes | Accepted direction | Workshop Milestones | Critical
2026-09-01 | Failure learning | Use failures, Q&A, and misunderstandings to create hands-on experience | Failure-card system and evidence-based investigation contract | Accepted direction | Lab Design | Critical
2026-09-01 | Calendar | Add a calendar artifact that maintains the story timeline | Dual learner/story timeline over a recommended 40-week journey | Accepted direction | Story Calendar | High
2026-09-01 | PLAN versus SSOT | PLAN is discussion; SSOT is final authority | Keep mutable planning and decision registers separate from locked files | Accepted direction | Governance | Critical

## Section Planning
Section Planning Board
Planning status, dependencies, priority, and lock readiness for every course section.
The first design target must be chosen explicitly after course-wide review and lab-network decisions.
Section | Title | Purpose | Units | Dependencies | Milestone | Planning status | Priority | SSOT state
00 | Computer and IT Prerequisites | Give an absolute beginner the computing mental models required before professional infrastructure work. | 10 | Ordinary computer use only | M00 | Design next | High | Draft discussion
01 | Evolution of Software Delivery | Show why modern DevOps practices emerged from earlier delivery and operations problems. | 6 | Section 00 | M00 | Design next | High | Draft discussion
02 | Software Development Life Cycle | Give the learner a complete view of how software moves from an idea to safe operation. | 7 | Sections 00-01 | M00 | Design next | High | Draft discussion
03 | VirtualBox and AnandTech Lab Platform | Build the persistent three-machine workshop environment used throughout the course. | 14 | Sections 00-02; supported host with virtualization enabled | M01 | Design next | High | Draft discussion
04 | Linux Foundations | Build the deepest foundational skill set in the course: observing, operating, and troubleshooting Linux systems. | 33 | Section 03 lab or continuity checkpoint | M02-M04 | Design next | High | Draft discussion
05 | Development Insight for DevOps Engineers | Teach enough modern application development for a DevOps engineer to understand what is built, tested, configured, deployed, and operated. | 17 | Section 04 Linux foundations or continuity checkpoint | M05 | Design next | High | Draft discussion
06 | Linux Networking | Teach the learner to reason about and troubleshoot communication from interface to application. | 8 | Sections 03-05 | M06 | Backlog | Medium | Draft discussion
07 | Shell Scripting and Automation | Turn repeated operational work into safe, observable, reusable automation. | 8 | Sections 04 and 06 | M07 | Backlog | Medium | Draft discussion
08 | Git and Source Control | Make every application and infrastructure change traceable and recoverable. | 7 | Section 07 | M08 | Backlog | Medium | Draft discussion
09 | Remote Git Collaboration | Teach professional team collaboration through remote repositories and review. | 6 | Section 08 | M08 | Backlog | Medium | Draft discussion
10 | SSH, SCP, SFTP, and Rsync | Operate systems and transfer release material securely. | 6 | Sections 03-09 | M09 | Backlog | Medium | Draft discussion
11 | Web Servers, HTTP, TLS, and Nginx | Deepen the learner's ability to operate the web entry point and request path. | 8 | Sections 05, 06, and 10 | M09 | Backlog | Medium | Draft discussion
12 | CI/CD Foundations and Jenkins | Transform manual build and release work into an evidence-producing pipeline. | 9 | Sections 08-11 | M10 | Backlog | Medium | Draft discussion
13 | Testing, Artifacts, and Automated Deployment | Build trustworthy releases that can be promoted, verified, and recovered. | 7 | Section 12 | M10 | Backlog | Medium | Draft discussion
14 | Monitoring, Logging, and Alerting | Ensure the team detects and investigates failures before customers must report them. | 7 | Sections 04-13 | M11 | Backlog | Medium | Draft discussion
15 | Containers, Docker, and Compose | Package the application and its runtime consistently while teaching the underlying Linux boundaries. | 10 | Sections 04-14 | M12 | Backlog | Medium | Draft discussion
16 | Ansible and Configuration Automation | Eliminate configuration drift across the persistent lab. | 8 | Sections 07, 10, and 15 | M13 | Backlog | Medium | Draft discussion
17 | Infrastructure as Code and Cloud Foundations | Teach infrastructure change as reviewed, reproducible, stateful code. | 8 | Sections 08, 09, and 16 | M14 | Backlog | Medium | Draft discussion
18 | AWS Foundations | Apply infrastructure, identity, networking, compute, storage, monitoring, security, and cost concepts in AWS. | 10 | Section 17; AWS account only when explicitly enabled | M14 | Backlog | Medium | Draft discussion
19 | Kubernetes and Orchestration | Teach desired-state workload orchestration after the learner understands Linux, networks, containers, and automation. | 11 | Sections 04, 06, 15-18 | M15 | Backlog | Medium | Draft discussion
20 | Observability, Reliability, and DevSecOps | Unify operational evidence, service reliability, incident response, and security across the delivery lifecycle. | 9 | Sections 12-19 | M16 | Backlog | Medium | Draft discussion
21 | Interview Preparation and Production Scenarios | Convert practical experience into clear technical reasoning and professional communication. | 8 | Progressive use throughout; full section after Section 20 | Portfolio | Backlog | Medium | Draft discussion
22 | Production CI/CD and AnandTech Capstone | Integrate the entire course into a production-style delivery and operations system. | 12 | Sections 00-21 | M17 | Backlog | Medium | Draft discussion

## Lab Planning
Lab Planning Board
Architecture proposals, progressive service ownership, risks, and dependencies.
The host-only IP decision is the highest-priority blocker because it changes every command, diagram, and workshop checkpoint.
Topic | Current proposal | Alternative / issue | Impact | Recommended resolution | Priority | Status
Host-only subnet | 192.168.56.0/24 | None | All lab communication | Retain | Critical | Accepted direction
Host address | 192.168.56.1 | Could be moved to .254 | Conflicts with requested web01 .1 | Retain .1 | Critical | Open
VM addresses | web01 .11; cicd01 .12; mon01 .13 | Requested .1/.2/.3 | All examples and diagrams | Use .11/.12/.13 | Critical | Open
Adapter 1 | Bridged | NAT fallback | Internet access and exposure | Use bridged primary with documented NAT fallback | High | Open
Adapter 2 | Host-only | None | Stable host and inter-VM management | Retain | Critical | Accepted direction
Persistent config | MAC-aware static host-only address | Interface names vary | Reboot reliability | Lock after distro network stack | High | Open
SSH | All VMs accessible from host | Initial password bootstrap only | All progressive workshops | Keys after bootstrap | Critical | Accepted direction
web01 | Alpine + Nginx + FastAPI | Containerization comes later | Development and web journey | Use native services first | High | Accepted direction
cicd01 | Debian + Git + Jenkins | Do not install before owning section | Git and pipeline journey | Progressive install | High | Accepted direction
mon01 | Debian + Prometheus + Grafana | Do not install before monitoring | Observability journey | Progressive install | High | Accepted direction
PostgreSQL/pgvector | Docker-hosted on learner host during development insight | Dedicated db01 not currently approved | Application persistence | Use supplied Compose checkpoint | High | Open
Recovery | Snapshots plus documented rebuild | Large distributed OVA files | Skippable failure labs | Use snapshots locally; ship scripts/configs | Medium | Open

## Workshop Planning
Workshop Journey Planning
Milestone goals, readiness, failure design, evidence, and skip-safe state.
Milestone IDs stay stable even if unit numbering changes; each section SSOT records the exact unlock unit.
ID | Journey event | Readiness | Practical mission | Failure design | Evidence | Skip checkpoint | Status
M00 | Anand's First Day | Sections 00-02 | Map the delivery system and responsibilities | Terminology mismatch and incomplete architecture | anandtech_delivery_map.md | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M01 | Build the AnandTech Lab | Section 03 Unit 14 | Build three persistent SSH-accessible VMs | IP conflict; interface order; two gateways; persistence; SSH | lab inventory; network map; recovery runbook | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M02 | Find the Evidence | Section 04 Unit 11 | Locate and interpret Linux configuration and logs | Case; comments; recursive noise; regex; ignored exit code | grep investigation; configuration inventory | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M03 | The Server Is Slow | Section 04 Unit 20 | Diagnose CPU, memory, load, disk, and inode symptoms | CPU process; memory pressure; full disk; inode exhaustion; deleted-open log | resource investigation; incident report | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M04 | Restore the Service | Section 04 Units 21-33 | Recover a failed systemd-managed service | Wrong service user; unreadable env; restart loop; Nginx upstream | service runbook; unit review; timeline | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M05 | Ship the First Todo Application | Section 05 | Build and operate HTML/CSS/JS + FastAPI + pgvector | CORS; wrong URL; API data; DB; proxy; persistence | architecture; handoff; app runbook | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M06 | Users Cannot Reach AnandTech | Section 06 | Trace and repair a network request path | Wrong IP; route; loopback bind; firewall; DNS; listener | network incident report | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M07 | Stop Repeating Yourself | Section 07 | Automate three-server health checks | Quoting; missing tools; partial output; false success; cron env | health script; automation runbook | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M08 | Recover the Lost Change | Sections 08-09 | Recover history and deliver through review | Wrong branch; uncommitted work; conflict; secret; force push | Git recovery; workflow evidence | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M09 | Secure Release Transfer | Sections 10-11 | Transfer, verify, activate, and roll back a release | Key permissions; host key; remote permission; partial copy; wrong root | transfer runbook; release manifest | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M10 | Build the Delivery Pipeline | Sections 12-13 | Build, test, package, deploy, verify, and recover | Test; dependency; Jenkins permission; credential; wrong artifact; false success | Jenkinsfile; pipeline; deployment evidence; rollback | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M11 | Detect Before the Customer Calls | Section 14 | Monitor the platform and respond to an alert | Unreachable target; bad scrape; misleading dashboard; noisy alert | monitoring inventory; alert runbook; dashboard review | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M12 | Containerize AnandTech | Section 15 | Package and operate frontend, API, and pgvector | Build context; env; immediate exit; missing volume; DNS; root | Dockerfile; compose; runbook | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M13 | Repair Configuration Drift | Section 16 | Restore desired state and prove idempotence | Package; service; template; permission; partial host failure | Ansible project; compliance report | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M14 | Rebuild from Code | Sections 17-18 | Provision and remove a secured cloud environment | State; permissions; exposure; destructive plan; dependency; cost | infrastructure; ADR; cost/cleanup report | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M15 | Survive a Workload Failure | Section 19 | Deploy, break, observe, and recover Kubernetes workloads | Pod; selector; DNS; probe; resources; rollout | manifests; Kubernetes runbook | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M16 | Production Incident Night | Section 20 | Correlate evidence and lead recovery at 02:13 | Latency; auth errors; recent release; incomplete evidence | incident; post-incident review; improvement plan | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion
M17 | AnandTech Production Launch | Section 22 | Integrate and defend the complete platform | Multi-layer production simulation | final portfolio and technical defense | Expected state; vocabulary; sample evidence; restoration path; no mastery claim | Draft discussion

## Open Questions
Open Questions and Required Decisions
Questions that materially change scope, lab commands, cost, packaging, or learner experience.
Resolve critical questions before drafting affected locked SSOTs.
ID | Decision | Question | Recommended option | Alternative | Impact | Priority | Status
Q-001 | Host-only IP allocation | Should the host retain 192.168.56.1 and VMs use .11/.12/.13? | Use .11/.12/.13 | Keep VM .1/.2/.3 and move host adapter | Lab connectivity and every downstream example | Critical | Open
Q-002 | Internet adapter | Should the primary course use bridged or NAT for Internet access? | Bridged as requested, with NAT fallback | NAT as safer default | Exposure, corporate Wi-Fi compatibility, screenshots | High | Open
Q-003 | Debian networking | Which Debian network stack is canonical for persistent interfaces? | systemd-networkd or /etc/network/interfaces after installer decision | NetworkManager | Exact commands and recovery labs | High | Open
Q-004 | Terraform | Is Terraform the locked IaC implementation tool? | Use Terraform | Keep tool-neutral until Section 17 planning | Section scope and examples | Medium | Open
Q-005 | AWS cost model | Will live AWS labs be mandatory or optional? | Optional with free-tier/cost guardrails | Mandatory account | Accessibility, cost, cleanup | High | Open
Q-006 | Workshop assets | Will the course distribute VM appliances/snapshots or only build instructions? | Build instructions plus checkpoint scripts/configs | Include large OVA/snapshot assets | Package size and maintenance | Medium | Open
Q-007 | Solutions | How should self-study workshop solutions be delivered? | Separate solution_after_attempt.md | Inline progressive hints only | Learning integrity and usability | Medium | Open
Q-008 | Calendar pace | Is 40 weeks the canonical recommended pace? | 40-week standard plus accelerated/self-paced views | Different fixed duration | Course positioning and workload | Medium | Open

## Decision Register
Planning Decision Register
Move a discussion here when a direction is accepted, rejected, deferred, or ready for SSOT drafting.
Accepted for SSOT means ready to be written into a draft SSOT; it still does not mean locked.
ID | Decision area | Proposed decision | Rationale | Affected sheets/sections | Status | Approval reference | Next action
D-001 | Course identity | Journey with AnandTech — DevOps Zero to Production | Explicit user direction | Course-wide | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-002 | Course model | Parallel story course plus optional milestone workshop track | Latest discussion | Course-wide | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-003 | Workshop skip behavior | Full, guided, or continuity checkpoint | Latest discussion | Labs | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-004 | Planning governance | PLAN records mutable discussions; SSOT contains final locked decisions | User instruction | Governance | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-005 | Linux depth | Linux is the deepest foundation with 33 units including grep and systemd | User instruction | Section 04 | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-006 | Development scope | HTML/CSS/JS Todo + FastAPI endpoints + Docker-hosted PostgreSQL/pgvector insight | User instruction | Section 05 | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-007 | VM roles | web01 Alpine; cicd01 Debian; mon01 Debian | User instruction | Lab | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-008 | VM networking | Adapter 1 bridged; Adapter 2 host-only; persistent; SSH from host | User instruction | Lab | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-009 | Host-only IPs | Recommend host .1 and VMs .11/.12/.13 instead of requested .1/.2/.3 | Avoid host/web01 duplicate address | Lab | Discussing | Conversation 2026-09-01 | Resolve choice
D-010 | VirtualBox automation | VBoxManage plus PowerShell, Python, Vagrant overview/examples | User instruction | Section 03 | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-011 | Progressive installation | Install/configure each tool in its owning section | User instruction | Course-wide | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-012 | Course calendar | Cumulative learner timeline and stable story timeline artifact | User instruction | Artifacts | Accepted for SSOT | Conversation 2026-09-01 | Write into relevant SSOT draft
D-013 | Terraform | Use Terraform as the proposed IaC teaching tool | Requires explicit technology lock | Section 17 | Discussing | Conversation 2026-09-01 | Resolve choice
D-014 | Bridged Internet adapter | Use bridged mode as requested; teach exposure and LAN dependence | NAT may be safer on restricted networks | Lab | Discussing | Conversation 2026-09-01 | Resolve choice

## Review Checklist
Planning-to-SSOT Review Checklist
Use before requesting explicit lock for the project map, lab design, or any section.
A blank or failed item prevents lock readiness; the owner records evidence rather than checking boxes from memory.
Area | Review question | Evidence required | Owner | Status | Notes
Scope | Are section purpose, outcomes, units, topics, exclusions, and dependencies explicit? | Completed scope map | Curriculum architect | Not started
Sequence | Does every unit rely only on previously taught or declared knowledge? | Dependency review | Learning reviewer | Not started
Lab | Are platform, software, permissions, starting state, network, cleanup, and recovery defined? | Lab manifest | Lab designer | Not started
Safety | Are privileged, disruptive, and destructive steps bounded and recoverable? | Safety review | Technical reviewer | Not started
Story | Does the AnandTech narrative create motivation and preserve chronology? | Story/calendar review | Instructional designer | Not started
Workshops | Are milestone readiness, modes, failure, evidence, recovery, and skip state defined? | Workshop contract | Lab designer | Not started
Artifacts | Does every required artifact have purpose, path, content, evidence, and completion criteria? | Artifact register | Curriculum architect | Not started
Assessment | Do assessments align with objectives and progress from recognition to engineering? | Assessment map | Learning reviewer | Not started
Technology | Are version-sensitive choices explicit and authorized? | Technology decision record | Technical reviewer | Not started
Packaging | Is the final package name and content boundary defined without granting packaging permission? | Package specification | Project owner | Not started
Conflict | Have all conflicts with higher-authority instructions been resolved visibly? | Decision register | Project owner | Not started
Lock | Has the user explicitly said the SSOT is locked? | Conversation reference | Project owner | Not started

## Change Log
PLAN Change Log
Append-only record of material planning revisions.
Future revisions should add rows with affected decisions instead of overwriting why the plan changed.
Version | Date | Change | Reason | Affected areas | Status
0.1 | 2026-09-01 | Initial course section/unit/topic draft | Establish complete zero-to-production map | All sections | Recorded
0.2 | 2026-09-01 | Expanded VirtualBox, Linux, and development insight | User requested deeper foundation and progressive real application | Sections 03-05; lab | Recorded
0.3 | 2026-09-01 | Added parallel workshop journey and course calendar | User requested industrial milestone labs and comic-like chronology | M00-M17; artifacts; story | Recorded
0.4 | 2026-09-01 | Created spreadsheet-based SSOT draft and PLAN register | Consolidate discussions into auditable planning artifacts | Governance; complete course | Current